## Work Groups
Work Group Name | Work Group | SD | FMG Liason | FMG Backup | Engagement Type | PSS? | Group Lead | Responsibility/Interest
Clinical Information Modeling Initiative | CIMI | N/A | Brian | Hugh | Consulted | N/A
Clinical Decision Support | CDS | SSD | Paul | Lorraine | Consulted | No |  | vMR
Clinical Genomics | CG | DESD | Brian | Lorraine | Developing | No | Amnon | Tentatively developing "Family History" resource
Clinical Interoperability Council | CIC | DESD | Paul | Hugh | Consulted | N/A |  | Not likely involved (governance structure) - but may use as a source for Requirements
Conformance & Guidance for Implementation / Testing | CGIT | FTSD | David | Lloyd | Consulted | N/A |  | Interested in Profile and Conformance resources
DICOM | DICOM | N/A | John M. | Hugh | Consulted | N/A |  | Interested in ImagingObservation
Education | Education | T3S | David | John M. | Consulted | N/A |  | FHIR tutorials, webinars, training videos, etc.
Electronic Services | ES | T3S | Lorraine | John M. | Consulted | N/A |  | Involved in providing website support/facilities, listserv support, etc
Electronic Health Record | EHR | SSD | Josh | David | Consulted | N/A |  | May eventually bind functional requirements to FHIR specs
FHIR Core Team | Core | N/A | Lloyd | David | Developing | ?? | Grahame | Responsible for all "infrastructure" resources
Financial Management | FM | SSD | Lloyd | Paul | Developing | No | Paul Knapp | Responsible for Coverage and likely other resources
Health Care Devices | Devices | DESD | David | Hugh | Consulted | N/A |  | Consulted on "Device" resource
IHE | IHE | N/A | John M. | David | Consulted | N/A | John M.? | Interested in XDS and ATNA-related resources
Imaging Integration | II | SSD | John M. | Lorraine | Consulted | N/A |  | Consulted on ImagingObservation. Conduit to DICOM participation
Implementable Technology Specifications | ITS | FTSD | Paul | Brian | Consulted | N/A |  | Interested in RESTful approach, XML and JSON syntaxes
Infrastructure & Messaging | InM | FTSD | David | Lloyd | Consulted | N/A |  | Interested in Message and IssueReport
Mobile Health | MH | SSD | Hugh | David | Consulted | N/A |  | Aim to create a conformance specification for standardization of interface between mobile devices and Electronic Health Records (EHR)/ Personal Health Records (PHR) systems. Starting 2013/Jan
Modeling & Methodology | MnM | FTSD | Lloyd | Josh | Developing | Complete | Lloyd | Responsible for methodology
Orders & Observations | OO | SSD | Lorraine | Brian | Developing | Complete | Lorraine Constable/Patrick Loyd | Responsible for several resources
Patient Administration | PA | SSD | Hugh | Brian | Developing | In progress | Alexander Henket | Responsible for several resources
Patient Care | PC | DESD | Lloyd | David | Consulted | N/A | Jean | Responsible for several resources
Pharmacy | Pharmacy | DESD | Hugh | Lloyd | Developing | Complete | Hugh | Responsible for several resources
Public Health Emergency Response | PHER | DESD | Lloyd | Lorraine | Developing | Yes | Joginder Madra | Tentatively committed for Immunization resource
Publishing | Publishing | T3S | Brian | Lorraine | Consulted | N/A |  | Minimal coordination needed for publication process
Regulated Clinical Research Information Management | RCRIM | DESD | Lloyd | Josh | TBD |  |  | Near term resource development potential
RIM-based Application Architecture | RIMBAA | FTSD | Josh | Hugh | Consulted | N/A |  | Interested in RIM mappings, implementation approach
Security | Security | FTSD | John M. | Brian | Consulted | N/A |  | Interested in Security section and SecurityEvent resource
Service Oriented Architecture | SOA | FTSD | David | Paul | Consulted | N/A |  | Interested in RESTful approach, services capabilities
Structured Documents | SD | SSD | David | Lloyd | Consulted | N/A |  | Interested in monitoring Document and related resources
Templates | Templates | FTSD | Brian | John M. | Consulted | N/A |  | Interested in Profile resource
Tooling | Tooling | T3S | Paul | Lloyd | Consulted | N/A |  | Need to transition FHIR publication and possibly other tools
US Realm Task Force | US | N/A | Lorraine | Paul | Consulted
Vocabulary | Vocab | FTSD | Lloyd | Hugh | Consulted | N/A |  | Interested in vocabulary datatypes, Profile binding mechanism and ValueSet resource
Not yet engaged
Anatomic Pathology |  | DESD | [5 empty] | Future resource development potential, though doesn't typically develop static model structures
Anesthesiology |  | DESD | [5 empty] | Future resource development potential, though doesn't typically develop static model structures
Attachments |  | DESD | [5 empty] | May eventually consider FHIR for use in attachment design
Child Health |  | DESD | [5 empty] | Future resource development potential, though doesn't typically develop static model structures
Community Based Collaborative Care | CBCC | DESD | [5 empty] | Near term resource development potential (consent, policy)
Emergency Care | EC | DESD | [5 empty] | Future resource development potential
Patient Safety | PS | DESD | [5 empty] | Future resource development potential
Arden Syntax | Arden | SSD | [5 empty] | May eventually be interested in FHIR for curly brackets potential
Clinical Context Object Workgroup | CCOW | SSD | [5 empty] | Could theoretically define resources for Context, etc., but unlikely
Clinical Decision Support |  | SSD | [5 empty] | ???
Clinical Statement |  | SSD | [5 empty] | Not likely involved (coordinating group, not developer of new content)
International Mentoring |  | T3S | [5 empty] | Not likely involved
Process Improvement |  | T3S | [5 empty] | Not likely involved
Project Services |  | T3S | [5 empty] | Not likely involved

## Resources
Resources to be complete for 1st DSTU | [10 empty] | 2013-10-02 | 2013-09-02
N/A | Draft | [9 empty] | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01
N/A | Complete | [9 empty] | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01
Category | Resource | Responsible Committee | Consulted Committee | Notes | Resource Proposal Author | Resource Proposal 1st Review | Resourvce Proposal 2nd Review | Resource Proposal Status? | Requirements | Status | Name | Definition | Scope | Content Sources | Example uses | Search Criteria | Core elements | Examples | Element definitions | Bindings | Requirements & Usage | Value Sets / Code Lists | Invariants | HTML files | Mappings
Clinical | AdverseReaction | Core | PC |  | Jean | Brian | Lorraine | Draft | CCDA | Draft | Complete | Complete |  |  |  | Draft | Complete | Draft | Draft | Draft |  | Started | Started | Started | Started
Clinical | Alert | Core | PC |  | David H. | ? | ? |  | ???? | Draft | 2013-04-01: Draft
Clinical | AllergyIntolerance | Core | PC | Ewout | Jean | Brian | David | Draft | CCDA | Draft
Technical | Binary | Core | ITS |  | N/A | n/a | n/a |  | Infrastructure | Semi-stable
Clinical | CarePlan | Core | PC | Lloyd | Lloyd | David | Brian | Draft | CCDA | Draft | Draft
_Introduction | Codes & Terminologies | Core: Core; PC: Vocab; Draft: Semi-stable
_Implementation | Common Usages | Core: Core; PC: EHR?; Draft: Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Clinical | Condition | Core | PC | Was Problem | David H. | John M | Brian | Draft | CCDA | Draft | Draft
Conformance | Conformance | Core | ICGT |  | Lloyd | Hugh | David | Draft | Infrastructure | Semi-stable
_Introduction | Datatypes | Core: Core; PC: Vocab; Draft: Semi-stable
Financial | Coverage | FM |  |  | Lloyd | Brian | Hugh | Draft | CCDA | Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Administrative | Device | OO |  |  | Lorraine | Hugh | Lloyd | Draft | Connectathon | Draft | Draft
Device Communications | DeviceCapabilities | Devices |  |  | Grahame | John M | Hugh | Draft | DICOM | Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Device Communications | DeviceLog | Devices |  |  | Grahame | John M | Hugh | Draft | DICOM | Draft | Complete | Draft | Draft | Draft
Device Communications | DeviceObservation | Devices |  |  | Grahame | John M | Hugh | Draft | DICOM | Draft | Draft | Started | Started | Started
Diagnostics | DiagnosticOrder | OO |  |  | OO | David | Hugh | Draft | ???? | Proposed | Draft | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Diagnostics | DiagnosticReport | OO |  |  | Lorraine | David | Brian | Draft | Connectathon | Semi-stable | Draft
Technical | DocumentReference | Core | IHE | Was XdsEntry, IndexEntry | John M. | Jean | Lorraine | Draft | IHE | Semi-stable | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
_Implementation | Documents | Core: Core; PC: SD; Draft: Semi-stable
Technical | DocumentRoot | Core | SD | Was Document | John M. | Jean | Lorraine | Draft | Infrastructure | Semi-stable | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
_Introduction | Extensibility | Core: Core; PC: ITS; Draft: Semi-stable | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Administrative | Encounter | PA | PC | Was Visit | Ewout - PA | Hugh | John M | Draft | CCDA | Draft
_Introduction | Formats | Core: Core; PC: ITS; Draft: Semi-stable | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Clinical | FamilyHistory | Core | CG |  | David H. | Lorraine | Brian | Draft | CCDA | Draft | Draft
Administrative | Group | Core | PA |  | Hugh - done | John M | Lloyd | Draft | Referenced by? | Semi-stable | Draft | Draft | Draft | Draft
Diagnostics | ImagingStudy | II |  |  | John M. | Brian | David | Draft | CCDA | Draft | Complete | Complete |  |  |  | Draft | Complete | Draft | Draft | Draft |  | Started | Started | Started | Started
Clinical | Immunization | PHER |  |  | PHER | Hugh | Lloyd | Draft | CCDA | Draft | Complete | Complete |  |  |  | Draft | Complete | Draft | Draft | Draft |  | Started | Started | Started | Started
_Implementation | Implementation | Core: Core; PC: ITS; Draft: Semi-stable
_Introduction | Introduction | Core: Core; Draft: Semi-stable | Draft | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Clinical | ImmunizationProfile | PHER |  |  | PHER | Brian | Lloyd | Draft | CCDA | Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Foundation | List | Core | PC |  | Hugh - done | Lorraine | Lloyd | Draft | CCDA | Semi-stable | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Administrative | Location | PA |  |  | Ewout - PA | David | Jean | Draft | CCDA | Proposed | Draft
Foundation | Media | II | OO | Was Picture | Hugh - done | Lorraine | John M | Draft | DICOM | Draft
Medications | Medication | Pharmacy |  |  | Hugh - done | Lorraine | John M | Draft | CCDA | Draft
Medications | MedicationAdministration | Pharmacy |  |  | Hugh - done | Lorraine | David | Draft | CCDA | Draft | Draft
Medications | MedicationDispense | Pharmacy |  |  | Hugh - done | John M | Jean | Draft | CCDA | Draft | Draft | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Medications | MedicationPrescription | Pharmacy |  | Was Prescription | Hugh - done | Lloyd | Jean | Draft | CCDA | Draft | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
_Implementation | Messaging | Core: Core; PC: InM; Draft: Semi-stable | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Medications | MedicationStatement | Pharmacy |  |  | Hugh - done | Brian | Lorraine | Draft | CCDA | Draft
Technical | MessageRoot | Core | InM | Was Message | Brian | Lloyd | David | Draft | Infrastructure | Semi-stable | Draft
Foundation | Observation | OO |  |  | Lorraine | Lloyd | Jean | Draft | CCDA | Draft | Draft
Technical | OperationOutcome | Core | InM | Was IssueReport | Lloyd - needs updating | Hugh | John M | Draft | Infrastructure | Semi-stable | Draft | Draft | Draft | Draft
Technical | Order | Core | OO | Was OrderRequest | OO | Lloyd | Hugh | Draft | Infrastructure | Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Technical | OrderResponse | Core | OO |  | OO | Hugh | Lloyd | Draft | Infrastructure | Draft | Complete | Complete |  |  |  | Draft | Complete | Draft | Draft | Draft |  | Started | Started | Started | Started
Administrative | Organization | PA |  |  | Ewout - PA | David | Jean | Draft | Header | Draft | Draft
Administrative | Patient | PA |  |  | Ewout - PA - needs updating | Lloyd | John M | Draft | Header | Draft | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Administrative | Practitioner | PA |  | Was Agent, Provider | Ewout - PA | Hugh | Lorraine | Draft | Header | Draft | Draft | Draft | Draft | Draft
Clinical | Procedure | Core | PC | Lloyd | David H. | Lorraine | Lloyd | Draft | CCDA | Draft | Draft
Conformance | Profile | Core | ICGT, Templates |  | Lloyd | Jean | David | Draft | Infrastructure | Semi-stable | Complete | Draft | Draft |  |  | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Foundation | Provenance | Core | Security, IHE |  | John M. | Jean | David | Draft | Infrastructure | Semi-stable | Draft | Started | Started | Started
Foundation | Query | Core: Core
Foundation | Questionaire | Core | OO |  | Ewout - PA | Lloyd | David | Draft | ???? | Draft | Draft
Administrative | RelatedPerson | PA |  |  | Ewout - PA | Hugh | John M | Draft | Header | Proposed
_Introduction | Resource Definitions | Draft: Semi-stable | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
_Implementation | REST (HTTP) | Core: Core; PC: ITS; Draft: Semi-stable | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
_Introduction | Roadmap | Core: Core; Draft: Semi-stable | Complete | Complete |  |  |  | Draft | Complete | Draft | Draft | Draft |  | Started | Started | Started | Started
_Implementation | Search/Query | Core: Core; PC: ITS; Draft: Semi-stable | Complete | Complete | Complete |  |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
_Implementation | Security | Core: Core; PC: Security; Draft: Draft
Technical | SecurityEvent | Core | Security, IHE |  | John M. | Jean | Lorraine | Draft | IHE | Semi-stable | Complete | Complete | Draft |  |  | Complete | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
Diagnostics | Specimen | OO |  |  | Lorraine | David | Brian | Draft | Referenced by lab report | Draft | Draft
Foundation | Substance | OO |  | Non-medication | Lorraine | David | Hugh | Draft | CCDA | Draft | Draft
Foundation | Supply | OO |  | Non-medication - Lloyd to review | Lorraine | Lloyd | Jean | Draft | CCDA | Draft | Draft
Conformance | ValueSet | Core | Vocab |  | Lloyd | Jean | Brian | Draft | Infrastructure | Semi-stable
Administrative | Animal | Core: PA; Ewout: Dropped; CCDA: ?; Draft: Dropped
Clinical | AssessmentScale | Core: Core; PC: PC; Ewout: drop?; CCDA: ?; Draft: Dropped
Foundation | Category | Core: Core; PC: IHE; Ewout: Was XdsFolder; CCDA: IHE; Draft: Dropped
Administrative | ConsentDirective | Core | CBCC, Security |  | John M. | ? | ? | Draft | ???? | Deferred
Clinical | InterestOfCare | Core: Core; PC: PC; Ewout: Need better name; CCDA: Referenced by various things; Draft: Deferred
Administrative | Person | Core: PA; Ewout: Dropped; CCDA: Header; Draft: Dropped
Clinical | Referral | Core: Core; PC: PC; Draft: Deferred

## Resource Headings
Resource Spreadsheet Heading Definitions
Column | Meaning
Category | Broad categorisation
Resource | Specific resource name
Responsible Committee | Committee who has primary responsibility
Consulted committee | Other committee with a significant interest
Notes | Anything general with no other home
Resource Proposal | Has the resource proposal been submitted and approved by FMG
Requirements | Have the requirements for the resource been identified and documented?
Status
Name | Has the name been agreed?
Definition | Is there an agreed definition for the resource?
Scope | Has the scope of the resource been specified?
Content Sources | Have the sources that are used as references for the attributes in the resources been dentified?
Example Uses | Have the example uses for the resource been identified?
Search Criteria | Have the search criteria been identified?
Core elements | Have the core elements of the resource been identified and add entered into the source spreadsheet?
Examples | Have one or more examples been created?
Element definitions | Has every element been defined?
Bindings | Has every element that uses vocabulary got a binding to a value set or code system?
Requirements & Usage | Has the requirement and usage of the element in the content sources been identified?
Value Sets / Code Lists | Where a binding has been identified has the content of the value set or code list been specified?
Invariants | Have all the constraints on the elements been specified? (Including writing xpath or ocl)
HTML files | Have additional notes been written using the introduction and notes source files?
Mappings | Have mappings to V3 RIM and V2 been provided?

## FMG Members
Members
Brian
David
Hugh
John M.
John Q.
Lloyd
Lorraine
Paul
Josh
Ron